## Tasks and Timeline (Gantt Chart
Sauce & Spoon Project Plan
PROJECT TITLE | Menu Tabletop Tablet Pilot Implementation: Sauce and Spoon | COMPANY NAME |  | Sauce & Spoon
PROJECT MANAGER | Kommomo Usang | DATE |  | 2025-05-27
Task | Notes | Start Date | Due Date | Duration (days) | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Initiate Project
Gather historical data on ordering process |  | 2025-05-01 | 2025-05-02 | 2 | Kommomo | 100% | bar: WEEK 1 R to WEEK 1 F
Research data points on restaurant tablet ordering systems |  | 2025-05-02 | 2025-05-02 | 1 | Kommomo | 100% | bar: WEEK 1 F
Calculate projections and enhancements |  | 2025-05-05 | 2025-05-05 | 1 | Kommomo | 100% | bar: WEEK 2 M
Align and evaluate stakeholders |  | 2025-05-06 | 2025-05-06 | 1 | Kommomo | 100% | bar: WEEK 2 T
Interview members of staff |  | 2025-05-07 | 2025-05-07 | 1 | Alex, Gilly | 100% | bar: WEEK 2 W
Determine how many tablets we need to order for each location |  | 2025-05-07 | 2025-05-07 | 1 | Alex, Gilly | 100% | bar: WEEK 2 W
Create project charter (scope and goals) |  | 2025-05-08 | 2025-05-09 | 2 | Kommomo | 100% | bar: WEEK 2 R to WEEK 2 F
Schedule kick-off meeting |  | 2025-05-12 | 2025-05-12 | 1 | bar: WEEK 3 M
Select a tablet vendor | [5 empty] | 100%
Research tablet features |  | 2025-05-13 | 2025-05-13 | 0 | Seydou | 100% | bar: WEEK 3 T
Confirm compatible OS |  | 2025-05-13 | 2025-05-13 | 0 | Kommomo | 100% | bar: WEEK 3 T
Compare tab pricing |  | 2025-05-13 | 2025-05-13 | 0 | Seydou | 100% | bar: WEEK 3 T
Connect the Sauce & Spoon marketing team to Terrific tab |  | 2025-05-14 | 2025-05-14 | 1 | Seydou | 100% | bar: WEEK 3 W
Plan Project
Generate quotes and review costs |  | 2025-05-15 | 2025-05-15 | 1 | Kommomo | 100% | bar: WEEK 3 R
Create contracts and SOW for vendors |  | 2025-05-16 | 2025-05-19 | 2 | Kommomo | 100% | bar: WEEK 3 F to WEEK 4 M
Book electrician for specific dates |  | 2025-05-19 | 2025-05-19 | 1 | Seydou | 100% | bar: WEEK 4 M
Vendor timeline and deliverables schedule |  | 2025-05-20 | 2025-05-21 | 2 | Kommomo | 100% | bar: WEEK 4 T to WEEK 4 W
Message about launch date to stakeholders |  | 2025-05-22 | 2025-05-22 | 1 | Deanna | 100% | bar: WEEK 4 R
Schedule staff meetings with the GM to discuss anything that could affect FOH staff tips and get their buy-in |  | 2025-05-23 | 2025-05-23 | 0 | Kommomo | 100% | bar: WEEK 4 F
Set a date for staff training at each location and update staff calendars |  | 2025-05-23 | 2025-05-23 | 0 | Kommomo | 100% | bar: WEEK 5 M
Draft a training plan |  | 2025-05-24 | 2025-05-25 | 2 | Kommomo | 100% | bar: WEEK 5 T to WEEK 5 W
Create launch day plan |  | 2025-05-26 | 2025-05-27 | 2 | Kommomo | 100% | bar: WEEK 5 R to WEEK 5 F
Project Plan updates |  | 2025-05-27 | 2025-05-27 | 1 | bar: WEEK 5 F
Tablet Installation & Integration
Make Payments for tabs |  | 2025-05-27 | 2025-05-28 | 2 | Kommomo | 100% | bar: WEEK 6 M to WEEK 6 T
Follow-up with Carter on menu |  | 2025-05-28 | 2025-06-03 | 5 | Carter | 100% | bar: WEEK 6 T to WEEK 7 M
Send menu & coupon information to designer to produce mock-ups to feature in tabs |  | 2025-06-04 | 2025-06-04 | 1 | Carter | 100% | bar: WEEK 7 T
Upload menu content to tablets |  | 2025-06-05 | 2025-06-05 | 0 | Seydou | 100% | bar: WEEK 7 W
Shipping & receiving tablets |  | 2025-06-05 | 2025-06-18 | 10 | Deanna | 100% | bar: WEEK 7 R to WEEK 9 W
Integrate tablet with POS system |  | 2025-06-19 | 2025-06-23 | 3 | Seydou | 100% | bar: WEEK 9 R to WEEK 10 M
Confirm POS status |  | 2025-06-23 | 2025-06-23 | 1 | Seydou | 100% | bar: WEEK 10 M
Implement a post-dining survey to assess customer satisfaction |  | 2025-06-24 | 2025-06-24 | 1 | Kommomo | 100% | bar: WEEK 10 T
Test the tablet |  | 2025-06-24 | 2025-06-24 | 1 | Seydou | 100% | bar: WEEK 10 T
Install tablet security | [5 empty] | 100%
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 2025-06-24 | 2025-06-24 | 1 | Deanna | 100% | bar: WEEK 10 T
Enable GPS location services on each tablet |  | 2025-06-24 | 2025-06-24 | 1 | Seydou | 100% | bar: WEEK 10 T
Create messaging about payment portal security to display on the tablets |  | 2025-06-24 | 2025-06-24 | 1 | Kommomo | 100% | bar: WEEK 10 T
Include payment security talking points in waitstaff training |  | 2025-06-24 | 2025-06-24 | 1 | Alex,Gilly | 100% | bar: WEEK 10 T
Complete Tablet Installation |  |  |  |  | Seydou | 100%
Upgrade wiring for electrical and Wi-Fi systems |  | 2025-06-25 | 2025-06-25 | 1 | Seydou | 100% | bar: WEEK 10 W
Purchase & Use protective Cases & accessories |  | 2025-06-24 | 2025-06-24 | 1 | Kommomo | 100% | bar: WEEK 10 T
Set up system to monitor battery life of tablet |  | 2025-06-24 | 2025-06-24 | 1 | Seydou | 100% | bar: WEEK 10 T
Recruit & Hire additional staff |  | 2025-06-26 | 2025-06-26 | 1 | Alex,Gilly | 100% | bar: WEEK 10 R
Complete Training & Launch Preparation
Follow-up with Gilly and Alex about staff meeting scheduling |  | 2025-06-26 | 2025-06-26 | 0 | Kommomo | 100% | bar: WEEK 10 R
Make devices ready for training |  | 2025-06-26 | 2025-06-26 | 0 | Seydou | 100% | bar: WEEK 10 R
Pre-training meeting to introduce tablets and changes to staff before training them on the tablets |  | 2025-06-27 | 2025-06-27 | 1 | Alex,Gilly | 100% | bar: WEEK 10 F
Train Managers |  | 2025-06-30 | 2025-07-01 | 2 | Deanna | 100% | bar: WEEK 11 M to WEEK 11 T
Train FOH/ wait staff and BOH staff to update the menu |  | 2025-07-01 | 2025-07-02 | 2 | Alex,Gilly | 100% | bar: WEEK 11 T to WEEK 11 W
Test-run tablet with family and friends |  | 2025-07-03 | 2025-07-03 | 1 | Kommomo | 100% | bar: WEEK 11 R
Create a troubleshooting/support plan |  | 2025-07-03 | 2025-07-03 | 1 | Alex,Gilly | 100% | bar: WEEK 11 R
Launch day |  | 2025-07-04 | 2025-07-04 | 1 | Kommomo | 100% | bar: WEEK 11 F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Initiate Project
Gather historical data on ordering process
Research data points on restaurant tablet ordering systems
Calculate projections and enhancements
Align and evaluate stakeholders
Interview members of staff
Determine how many tablets we need to order for each location
Create project charter (scope and goals)
Schedule kick-off meeting
Select a tablet vendor
Research tablet features
Confirm compatible OS
Compare tab pricing
Connect the Sauce & Spoon marketing team to Terrific tab
Plan Project
Generate quotes and review costs
Create contracts and SOW for vendors
Book electrician for specific dates
Vendor timeline and deliverables schedule
Message about launch date to stakeholders
Schedule staff meetings with the GM to discuss anything that could affect FOH staff tips and get their buy-in
Set a date for staff training at each location and update staff calendars
Draft a training plan
Create launch day plan
Project Plan updates
Tablet Installation & Integration
Make Payments for tabs
Follow-up with Carter on menu |  | 1 | 0.5 | 1 | 2
Send menu & coupon information to designer to produce mock-ups to feature in tabs | the risk and dependency here is that Carter wants to revamp before he finalizes the menu and coupon information for the tablet content before sending. Carter's schedule can be unpredictable so we don't know when he can complete this. Speak to Carter about timeline so he can speed up | 10 | 7 | 10 | 14
Upload menu content to tablets | Depends on when mockups are ready . Takes 3-4 hours to upload once mockups are released | 3-4hrs | 3 hrs | 4hrs
Shipping & receiving tablets | D- Payment have to be made and content uploaded to tabs. Risks -Broken devices and shipping delay | 10 | 7 | 10 | 14
Integrate tablet with POS system | Depen - confirm that Sauce & Spoon is running POS version 3.0 and above. Risks - Sauce & Spoon may not be running version 3.0 of their POS software and as such may need to update their POS system by contacting Flatplate | 3 | 0.5 | 3 | 5
Confirm POS status
Implement a post-dining survey to assess customer satisfaction
Test the tablet
Install tablet security
Create a procedure for securing tablets at the end of the night (at the table or in a safe)
Enable GPS location services on each tablet
Create messaging about payment portal security to display on the tablets
Include payment security talking points in waitstaff training
Complete Tablet Installation | 16 hours.. Use 2 half days so they don't shut down for a full day
Upgrade wiring for electrical and Wi-Fi systems
Purchase & Use protective Cases & accessories
Set up system to monitor battery life of tablet
Recruit & Hire additional staff
Complete Training & Launch Preparation
Follow-up with Gilly and Alex about staff meeting scheduling
Make devices ready for training
Pre-training meeting to introduce tablets and changes to staff before training them on the tablets | 1 hour at each location | 1 | 1hr
Train Managers | 2 hr for training and 1 hr for faciliator prep. Seydou trains managers | 1 | 3hr
Train FOH/ wait staff and BOH staff to update the menu | managers trains other staff | 1 | 3hr
Train customers for acceptance & usability
Create a troubleshooting/support plan
Test-run tablet with family and friends

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Restaurant tablet best practices, what’s the industry standard | https://solink.com/resources/industry-insights/restaurant-tablet-best-practices/#elementor-toc__heading-anchor-4 | 2025-06-20
Tablet Menu: 5 Reasons Why You Should Do The Switch | https://www.menutiger.com/blog/tablet-menu | 2025-06-20
Developing a Restaurant Tablet Implementation Plan for Success | https://madmobile.com/blog/challenges-of-implementing-restaurant-table-ordering/ | 2025-06-20
Possible Tasks for launching a tabletop tablet restaurant project. | https://www.linkedin.com/pulse/possible-tasks-launching-tabletop-tablet-restaurant-project-irodinjo/ | 2025-06-20
Tabletop tech speeds up service and boosts profits, study says | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ | 2025-06-20
The Impact of Restaurant Tablets on Table Turnover and Revenue | https://madmobile.com/blog/impact-of-restaurant-tablets-on-table-turnover-and-revenue/

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Average ticket time : appetizers-8mins; entrees-12-15mins | How can we improve ticket times? | Ticket times | FALSE
Customer Satisfaction | Order accuracy: 100% | Should we continue using tablets | Order accuracy | FALSE
Customer Satisfaction | Check out time: < 1min | Are customers satisfied with checkout processes | Satisfaction score | FALSE
Customer Satisfaction | Technical Issues: <5% reported | How can we improve customers' ability to use the tablets? | Technical issues reports | FALSE
Customer Satisfaction | Wait time: <10min | How can we reduce customer wait times | Average guest wait times | FALSE
Customer Satisfaction | >=75% Staff performance rating | To what extent do tablets reduce reliance on staff for order-taking? | Need for staff interaction | FALSE
Customer Satisfaction | Avg Post-order ratings >=4 out of 5 stars | Do customers find the menu tablets easy and enjoyable to use? | Technology adoption rate | FALSE
Customer Satisfaction | >=75% subscription rate to loyalty program | What is the frequency of guest visits, and does tablet usage affect return visits? | Subscription rate to loyalty program/return visits | FALSE
Customer Satisfaction | Increased upsells & add-ons | What types of menu items are most frequently selected via the tablet interface? | Ordering behaviour patterns | FALSE
Customer Satisfaction | <3 issues per 100 tablet uses | How often do customers encounter technical issues while using the tablet? | No of technical issues | FALSE
Customer Satisfaction | >=70% ease of navigation score | Do customers find it easy to navigate the tablet? | Ease of navigation | FALSE
Customer Satisfaction | Avg Satisfaction score>=70% | What is the overall guest satisfaction with the tablet system?" | Satisfaction score | FALSE
Customer Satisfaction | >=70% of customers prefer tablet | How does the tablet-based service compare to traditional waiter service in terms of guest satisfaction? | Comparative satisfaction rating | FALSE
Customer Satisfaction | Positive themes appear in >=60% of comments | What aspects of the tablet system enhance the guest experience? | Positive themes (speed, ease-of-use, convenience,visual design) | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Customer experience | To what extent are customers using the tablet to place additional or follow-up orders during their visit? | Tablet engagement rate | Did you use the tablet to put in multiple orders while you were dining? | Yes/No | Yes | No
Customer experience | What types of menu items are most frequently selected via the tablet interface? | Ordering behaviour patterns | During your visit, what did you order? Choose all that apply. | Multiple choice | Drinks | Appetizers | Dinner | Dessert
Customer experience | How can we improve ticket times | Average ticket time | How long did it take from placing your order on the tablet to receiving your food? | Scaled | 0-20 mins | 21-30 mins | 31-40 mins | 41-50mins | 50+mins
Customer experience | How can we reduce customer wait times | Average guest wait time | On average, how long did you wait for your table? | Scaled | 0-5 min | 6-10 mins | 11-15 mins | 15+mins
Customer experience | Should we continue using tablets? | Order accuracy | Did the kitchen prepare your order correctly? | Yes/No | Yes | No | If not, what went wrong?
Customer experience | How often do customers encounter technical issues while using the tablet? | Technical issues report | Did you encounter any technical issues while using the tablet? | Yes/No | Yes | No | If yes, please specify
Customer experience | Do customers find it easy to navigate the tablet? | Ease of navigation | On a scale of 1-5, how easy was it to use the tablet navigation | Scaled | Very easy | Fairly easy | Neutral | Slightly difficult | Difficult
Customer experience | Are customers satisfied with checkout processes | Agreement rating/ Satisfaction score | How would you respond to the following sentence: “I found the checkout process quick, easy, and secure.” | True/False | TRUE | FALSE | If you don't agree with the above statement, why?
Customer experience | What is the overall guest satisfaction with the tablet system?" | Satisfaction score | On a scale of 1-5, please rate your experience with the tablet overall | Scaled | Excellent | Good | Neutral | Poor | Very Poor
Customer experience | To what extent do tablets reduce reliance on staff for order-taking? | Staff performance rating | How well did your waiter instruct you how to use the tablet? | Multiple choice | Very well | ok | Not well
Customer experience | How does the tablet-based service compare to traditional waiter service in terms of guest satisfaction? | Comparative satisfaction rating | How would you rate this experience vs. a traditional experience with a waiter? | Multiple choice | Tablet | Waiter | A mix of both | no preference
Customer experience | How user-friendly and intuitive is the tablet menu for placing orders? | Technology adoption rate | How easy was it to order directly from the menu on the tablet? | Scaled | Very easy | Easy | Neutral | Slightly difficult | Difficult
Customer experience | To what extent do guests feel secure and confident using the tablet for payment? | Confidence Rating Score | How confident are you in submitting your payment through a tablet? | Scaled | Not at all | Somewhat | Neural | Confident | Very confident
Customer experience | How effective is the tablet at encouraging customers to subscribe to the newsletter? | Percentage who subscribe | Did you subscribe to the newsletter on the tablet? | Yes/No | Yes | No
Customer experience | How effective is the tablet at driving sign-ups for the birthday club loyalty program? | Percentage who subscribe | Did you subscribe to the birthday club? | Yes/No | Yes | No
Customer experience | What aspects of the tablet system enhance the guest experience? | Positive themes (speed, ease-of-use, convenience,visual design) | Please tell us anything else about your experience with our new tablet ordering system: | Open-ended
Customer experience | What areas of the tablet system or overall guest experience need improvement? | Recurring issues, no of guest mentions | What improvements would you suggest to enhance the tablet or your dining experience at Sauce & Spoon? | Open-ended