## Slide 1: Executive Summary
To support Sauce & Spoon’s growth and expansion goals, we introduced tabletop tablet menus at the Downtown and North locations, going live to guests on October 15. The project addressed a clear operational need: reduce service delays, improve order accuracy, and elevate the overall dining experience through digital innovation. Following the successful sourcing and installation of devices, staff were trained, and a pilot launch was conducted. Real-time customer feedback collected through on-tablet surveys guided several operational improvements, including continued waitstaff training, routine tablet functionality audits, and closer monitoring of food waste trends.
The outcomes have been significant:
Guest volume increased by 10%, and sales rose by over 20% since launch.
Wait times dropped by 30 minutes, checkout times were reduced to one minute, and food waste was cut in half.
Customer satisfaction improved from 72% post-pilot to 86% today, confirming a strong alignment with guest expectations.
Despite this success, we identified key opportunities for growth: earlier onboarding for staff could have accelerated adoption, and a more streamlined design-review process may have prevented initial user interface inconsistencies.
Next steps include refining the tablet experience based on ongoing feedback and developing a scalable implementation plan to roll out tablets across additional Sauce & Spoon locations. These results underscore the value of digital transformation in hospitality and position us well for future investment and expansion.